## GANTT
PROJECT TITLE: Analysis of current roles in data science using NLP techniques |  |  | T1 | [12 empty] | T2 | [12 empty] | T3 | [5 empty] | T4
|  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |  | JUL |  |  |  | AUG | SEP | OCT | NOV | DEC
|  |  | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 24 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27
1 | Project kick-off | Objectives definition | bar: FEB 10 to FEB 24
Project tentative proposal | bar: FEB 17 to MAR 2
2 | Theoretical framework | Literature review on data science roles | bar: FEB 17 to MAR 2
Analyze data science professional profiles | bar: FEB 24 to MAR 16
¦-> Consulting companies | bar: MAR 2
¦-> Standards Organizations | bar: MAR 9
¦-> Industry Organizations | bar: MAR 16
Summary report on data science roles | bar: MAR 16
3 | Data-driven approach | Literature review on NLP techniques | bar: MAR 23 to APR 13
Programming tools and libraries | bar: MAR 23 to APR 13
Design of experiments | bar: APR 6 to APR 13
Data scraping | bar: APR 6 to APR 20
Creation of dataset | bar: APR 6 to APR 20
Data exploration | bar: APR 13 to MAY 4
Data analysis | bar: APR 13 to MAY 4
4 | Results Discussion | Documentation of experiments | bar: MAY 4 to MAY 11
Summarise experiment insights | bar: MAY 11 to MAY 18
Compare empirical vs theoretical approach | bar: MAY 11 to MAY 18
5 | Final report | Presentation of results | bar: MAY 24 to JUN 1
Final report | bar: MAY 24 to JUN 1